## Ground Contacts
HTS-1 Ground Station Contact Schedule
Pass | Date (UTC) | Station | Band | AOS | LOS | Dur (min) | Max elev (deg) | Purpose | Status | Pass note | Station | Passes | Total min
101 | 2026-07-01 | Kourou | S | 03:12 | 03:46 | 34 | 71 | Post LV-sep state vector downlink | Complete |  | Kourou | 18 | 577
102 | 2026-07-01 | Hartebeesthoek | S | 09:48 | 10:12 | 24 | 52 | Ranging + Doppler | Complete |  | Hartebeesthoek | 12 | 319
103 | 2026-07-01 | Dongara | S | 14:03 | 14:12 | 9 | 11 | Health check | Partial | Horizon mask, lost lock at 3 deg | Dongara | 8 | 161
104 | 2026-07-01 | Kourou | X | 19:26 | 19:59 | 33 | 78 | Recorder dump, LV-sep event data | Complete |  | Svalbard | 6 | 97
105 | 2026-07-02 | Svalbard | S | 01:55 | 02:16 | 21 | 34 | Cmd upload, ADCS bias table | Complete |  | Santiago | 5 | 64
106 | 2026-07-02 | Hartebeesthoek | S | 08:31 | 09:04 | 33 | 63 | Maneuver cal downlink | Complete |  | Aperture total |  | 1218
107 | 2026-07-02 | Santiago | S | 13:47 | 13:59 | 12 | 19 | Health check | Complete
108 | 2026-07-02 | Kourou | S | 20:04 | 20:41 | 37 | 74 | State vector downlink | Complete |  | S-band passes |  | 43
109 | 2026-07-03 | Dongara | S | 02:39 | 03:01 | 22 | 44 | RWA momentum dump | Complete |  | X-band passes |  | 6
110 | 2026-07-03 | Hartebeesthoek | S | 09:11 | 09:40 | 29 | 58 | Ranging | Complete |  | Passes not fully supported |  | 3
111 | 2026-07-03 | Kourou | X | 18:52 | 19:23 | 31 | 76 | Payload bus checkout | Complete
112 | 2026-07-04 | Svalbard | S | 01:18 | 01:34 | 16 | 28 | Health check | Complete
113 | 2026-07-04 | Kourou | S | 07:44 | 08:14 | 30 | 68 | Maneuver cal downlink | Complete
114 | 2026-07-04 | Kourou | S | 12:06 | 12:06 | 0 | 22 | Ranging | Scrubbed | No AOS, station conflict with GSAT-19
115 | 2026-07-04 | Hartebeesthoek | S | 17:35 | 18:01 | 26 | 49 | State vector downlink | Complete
116 | 2026-07-05 | Dongara | S | 00:52 | 01:09 | 17 | 38 | Cmd upload | Complete
117 | 2026-07-05 | Kourou | S | 06:29 | 07:08 | 39 | 73 | Apogee burn readiness review data | Complete
118 | 2026-07-05 | Santiago | S | 11:58 | 12:14 | 16 | 23 | Health check | Complete
119 | 2026-07-05 | Hartebeesthoek | X | 16:41 | 17:11 | 30 | 75 | Recorder dump | Complete
120 | 2026-07-06 | Svalbard | S | 00:07 | 00:26 | 19 | 31 | Ranging | Complete
121 | 2026-07-06 | Kourou | S | 05:33 | 06:11 | 38 | 70 | State vector downlink | Complete
122 | 2026-07-06 | Dongara | S | 10:49 | 11:09 | 20 | 45 | RWA momentum dump | Complete
123 | 2026-07-06 | Hartebeesthoek | S | 15:20 | 15:45 | 25 | 55 | Maneuver cal downlink | Complete
124 | 2026-07-06 | Kourou | S | 21:02 | 21:33 | 31 | 64 | Cmd upload, burn timeline load | Complete
125 | 2026-07-07 | Santiago | S | 04:16 | 04:27 | 11 | 17 | Health check | Complete
126 | 2026-07-07 | Kourou | S | 09:38 | 10:22 | 44 | 81 | Apogee insertion, pre-burn quiescent | Complete | Extended pass, requested by GN&C
127 | 2026-07-07 | Kourou | X | 10:22 | 11:06 | 44 | 84 | Apogee insertion, burn coverage | Complete | Continuous coverage through burn
128 | 2026-07-07 | Hartebeesthoek | X | 11:14 | 11:50 | 36 | 79 | Apogee insertion, post-burn dump | Complete
129 | 2026-07-07 | Dongara | S | 16:47 | 17:11 | 24 | 41 | Post-burn state vector | Complete
130 | 2026-07-07 | Svalbard | S | 22:03 | 22:18 | 15 | 26 | Health check | Complete
131 | 2026-07-08 | Kourou | S | 03:31 | 04:00 | 29 | 66 | Payload separation coverage | Complete
132 | 2026-07-08 | Hartebeesthoek | S | 08:56 | 09:18 | 22 | 48 | Post-sep attitude recovery | Complete
133 | 2026-07-08 | Santiago | S | 14:12 | 14:25 | 13 | 21 | Ranging | Complete
134 | 2026-07-08 | Kourou | S | 19:44 | 20:17 | 33 | 61 | Orbit determination pass 1 of 3 | Complete
135 | 2026-07-09 | Dongara | S | 02:18 | 02:43 | 25 | 36 | Orbit determination pass 2 of 3 | Complete
136 | 2026-07-09 | Hartebeesthoek | S | 07:51 | 08:15 | 24 | 53 | Orbit determination pass 3 of 3 | Complete
137 | 2026-07-09 | Kourou | S | 13:27 | 13:53 | 26 | 59 | GEO trim burn timeline load | Complete
138 | 2026-07-09 | Svalbard | S | 18:40 | 18:50 | 10 | 13 | Health check | Partial | Rain fade, degraded margin
139 | 2026-07-10 | Kourou | S | 01:04 | 01:32 | 28 | 69 | GEO trim burn coverage | Complete
140 | 2026-07-10 | Hartebeesthoek | S | 06:22 | 06:49 | 27 | 46 | Post-trim state vector | Complete
141 | 2026-07-10 | Dongara | S | 12:47 | 13:08 | 21 | 33 | Ranging | Complete
142 | 2026-07-10 | Kourou | X | 17:58 | 18:26 | 28 | 72 | Recorder dump | Complete
143 | 2026-07-11 | Santiago | S | 03:35 | 03:47 | 12 | 18 | Health check | Complete
144 | 2026-07-11 | Hartebeesthoek | S | 08:14 | 08:37 | 23 | 51 | Station acquisition, longitude drift check | Complete
145 | 2026-07-11 | Kourou | S | 15:41 | 16:19 | 38 | 67 | Cmd upload, disposal timeline | Complete | Added late, replaced scrubbed pass 114
146 | 2026-07-12 | Svalbard | S | 00:29 | 00:45 | 16 | 29 | Health check | Complete
147 | 2026-07-12 | Kourou | S | 06:58 | 07:32 | 34 | 65 | Disposal burn coverage | Complete
148 | 2026-07-12 | Hartebeesthoek | S | 12:35 | 12:55 | 20 | 43 | Post-disposal state vector | Complete
149 | 2026-07-12 | Dongara | S | 19:07 | 19:30 | 23 | 39 | Final health check, end of mission | Complete

## Telemetry Channels
HTS-1 Telemetry Channel List
Channel | Subsystem | Description | Unit | Low | High | Type
PRP_TKP_F | Propulsion | Fuel tank pressure | psia | 180 | 310 | AN
PRP_TKP_O | Propulsion | Ox tank pressure | psia | 180 | 310 | AN
PRP_TKT_F | Propulsion | Fuel tank temp | degC | 10 | 45 | AN
PRP_TKT_O | Propulsion | Ox tank temp | degC | 10 | 45 | AN
PRP_VLV_1 | Propulsion | Main valve 1 state | - | 0 | 1 | BL
PRP_VLV_2 | Propulsion | Main valve 2 state | - | 0 | 1 | BL
PRP_HE_P | Propulsion | Pressurant (He) pressure | psia | 0 | 4000 | AN
PRP_CHMB_P | Propulsion | Chamber pressure | psia | 0 | 200 | AN
RCS_THR_T | Propulsion | RCS catbed temp | degC | 0 | 500 | AN
RCS_VLV_A | Propulsion | RCS valve A state | - | 0 | 1 | BL
EPS_BUSV | Power | Bus voltage | V | 26 | 30 | AN
EPS_BATT_SOC | Power | Battery state of charge | % | 0 | 100 | AN
EPS_BATT_T | Power | Battery temperature | degC | -5 | 40 | AN
EPS_SA_I | Power | Solar array current | A | 0 | 30 | AN
GNC_RWA1 | ADCS | Reaction wheel 1 speed | rpm | -6000 | 6000 | AN
GNC_RWA2 | ADCS | Reaction wheel 2 speed | rpm | -6000 | 6000 | AN
GNC_RWA3 | ADCS | Reaction wheel 3 speed | rpm | -6000 | 6000 | AN
GNC_RWA4 | ADCS | Reaction wheel 4 speed | rpm | -6000 | 6000 | AN
GNC_STR1 | ADCS | Star tracker 1 valid | - | 0 | 1 | BL
GNC_STR2 | ADCS | Star tracker 2 valid | - | 0 | 1 | BL
GNC_IMU_T | ADCS | IMU temperature | degC | -10 | 55 | AN
THM_RAD1 | Thermal | Radiator 1 temp | degC | -40 | 60 | AN
THM_RAD2 | Thermal | Radiator 2 temp | degC | -40 | 60 | AN
THM_HTR_1 | Thermal | Heater 1 duty | % | 0 | 100 | AN
COM_SBND_RSSI | Comms | S-band receive level | dBm | -120 | -60 | AN
COM_SBND_LCK | Comms | S-band lock | - | 0 | 1 | BL
COM_XBND_PWR | Comms | X-band TX power | W | 0 | 70 | AN
CDH_CPU_LD | C&DH | CPU load | % | 0 | 100 | AN
CDH_MEM_USE | C&DH | Memory usage | % | 0 | 100 | AN
CDH_SEU_CNT | C&DH | SEU counter | - | 0 | 65535 | AN

## Maneuver Plan
HTS-1 Mission Maneuver Plan (current)
Item | Maneuver ID | Phase | Description | Delta-V | UoM | Rev | Engine
1 | M1 | Phasing | Phasing burn | 120 | m/s | -001 | Main
2 | M2 | Transfer | Combined apogee insertion (circularize + plane change) | DERIVE | m/s | -002 | Main
3 | M3 | On-station | GEO trim/station acquisition | 115 | ft/s | -001 | Main
4 | M4 | Disposal | Disposal to graveyard orbit | DERIVE | m/s | -001 | Main
Subtotal of the burns already sized. The two DERIVE rows are not in it, they still have to be computed from the orbit parameters.
Maneuver | dV (m/s)
M1 phasing | 120
M3 GEO trim | 35.05 | ft/s off the old GN&C memo, converted here
Subtotal | 155.05

## Orbit Parameters
HTS-1 Orbit Parameters
Parameter | Symbol | Value | Unit | Note
Earth gravitational parameter | mu | 398600.4418 | km^3/s^2 | two body
Earth equatorial radius | Re | 6378.137 | km
GTO drop-off perigee altitude | hp | 200 | km | from launch vehicle ICD
GTO apogee altitude (= GEO) | ha | 35786 | km | apogee at GEO radius
GTO drop-off inclination | i_gto | 27 | deg | to be removed at apogee
Target orbit | - | GEO circular equatorial | - | i = 0 deg
Graveyard altitude above GEO | d_alt | 300 | km | disposal, two-burn Hohmann
Standard gravity | g0 | 9.8066 | m/s^2 | for Isp -> Ve
Radii the burn sizing keys off. Both are altitude plus Re.
GTO perigee radius Rp | 6578.14 | km
GTO/GEO apogee radius Ra | 42164.14 | km