## Obligation Register
Contract MER-2025-0087 ¦ Obligation deadline calendar ¦ CY2025
# | ID | Obligation | Party | Basis | Due date | Weekday
1 | O2 | First monthly invoice issued | Provider | Within 5 business days after the Effective Date | 2025-01-23 | Thu
2 | O1 | Project kickoff meeting | Provider | Within 10 calendar days after the Effective Date; roll to next business day | 2025-01-27 | Mon
3 | O6 | Certificate of insurance delivered | Provider | Within 15 calendar days after the Effective Date; roll to next business day | 2025-01-30 | Thu
4 | O8.1 | Monthly status report | Provider | By the 5th of each month; roll to next business day | 2025-02-05 | Wed
5 | O3 | Statement of Work sign-off | Client | Within 30 calendar days after the Effective Date; roll to next business day | 2025-02-14 | Fri
6 | O8.2 | Monthly status report | Provider | By the 5th of each month; roll to next business day | 2025-03-05 | Wed
7 | O11 | Integration report | Provider | Within 20 business days after the Statement of Work sign-off (chained to O3's due date) | 2025-03-17 | Mon
8 | O4.1 | Quarterly business review | Both | 3 business days before each calendar quarter-end | 2025-03-26 | Wed
9 | O12 | Independent security review | Provider | Within 75 calendar days after Effective Date; only if data classification is High (Exhibit B) | 2025-03-31 | Mon
10 | O8.3 | Monthly status report | Provider | By the 5th of each month; roll to next business day | 2025-04-07 | Mon
11 | O9 | Termination true-up statement | Provider | Within 45 calendar days after Amendment No.1 effective date (new) | 2025-04-17 | Thu
12 | O8.4 | Monthly status report | Provider | By the 5th of each month; roll to next business day | 2025-05-05 | Mon
13 | O8.5 | Monthly status report | Provider | By the 5th of each month; roll to next business day | 2025-06-05 | Thu
14 | O4.2 | Quarterly business review | Both | 3 business days before each calendar quarter-end | 2025-06-25 | Wed
15 | O8.6 | Monthly status report | Provider | By the 5th of each month; roll to next business day | 2025-07-07 | Mon
16 | O5 | Annual audit support package | Provider | By July 31; required only if total annual fees exceed $250,000 | 2025-07-31 | Thu
17 | O8.7 | Monthly status report | Provider | By the 5th of each month; roll to next business day | 2025-08-05 | Tue
18 | O7A | Non-renewal notice (as amended) | Either | At least 90 business days before Dec 31 (Amendment No.1) | 2025-08-21 | Thu
19 | O8.8 | Monthly status report | Provider | By the 5th of each month; roll to next business day | 2025-09-05 | Fri
20 | O4.3 | Quarterly business review | Both | 3 business days before each calendar quarter-end | 2025-09-25 | Thu
21 | O8.9 | Monthly status report | Provider | By the 5th of each month; roll to next business day | 2025-10-06 | Mon
22 | O8.10 | Monthly status report | Provider | By the 5th of each month; roll to next business day | 2025-11-05 | Wed
23 | O8.11 | Monthly status report | Provider | By the 5th of each month; roll to next business day | 2025-12-05 | Fri
24 | O4.4 | Quarterly business review | Both | 3 business days before each calendar quarter-end | 2025-12-26 | Fri
|  |  |  | Total active dated rows | 24

## Anchors and Holidays
Key dates, facts, and the holiday calendar
Holiday calendar
Effective Date | 2025-01-15 | 2025-01-01 | New Year's Day
Amendment No.1 Date | 2025-03-03 | 2025-01-20 | MLK Day
Total annual fees | 312000 | 2025-02-17 | Presidents Day
Processes personal data | No | 2025-05-26 | Memorial Day
Data classification (Exhibit B) | High | 2025-06-19 | Juneteenth
|  | 2025-07-04 | Independence Day
|  | 2025-09-01 | Labor Day
|  | 2025-11-27 | Thanksgiving
|  | 2025-11-28 | Day after Thanksgiving
|  | 2025-12-25 | Christmas Day

## Dropped
Obligations not on the calendar (with reason)
ID | Obligation | Reason
O7 | Non-renewal notice (original 60 business days) | Superseded: Amendment No.1 deletes Section 7.2 in its entirety and replaces the 60 with 90 business days (see O7A).
O10 | Data-protection breach drill | Condition not met: applies only if the Provider Processes Personal Data; the recital states it does not.